## Gantt
PROJECT TITLE | [5 empty] | Legend:
Team Members: | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
|  | Project Start Date: |  | 2023-09-17
|  | Display Week: |  | 1 |  | September | [13 empty] | October | [34 empty] | November
 | time axis 2023-09-18 to 2023-11-12
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
Milestone Description | Category | Assigned To | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
PROJECT PROPOSAL
Project Background and Description | Goal | Gurpreet Kaur | 100% | 2023-09-17 | 1
Problem Statement | Milestone | Pooja | 100% | 2023-09-18 | 1 | bar: Week 1 M
Project Scope | Low Risk | Shivam | 100% | 2023-09-19 | 1
High-Level Requirements | Milestone | sulika | 100% | 2023-09-20 | 1 | bar: Week 1 W
Materials, Tools Required | Med Risk | sulika | 100% | 2023-09-22 | 2
References Used |  | Pooja
REQUIREMENTS AND SPECIFICATIONS
Purpose | High Risk | Shivam | 100% | 2023-09-25 | 1
Overall Description | On Track | pooja | 100% | 2023-09-26 | 1
System Features | Low Risk | Gurpreet Kaur | 100% | 2023-09-27 | 1
External Interface Requirements | Milestone | sulika | 100% | 2023-09-28 | 1 | bar: Week 2 T
Non-Functional Requirements | Low Risk | pooja | 100% | 2023-09-29 | 1
References Used |  | Shivam | 100%
RISK BASED TEST STRATEGY
Purpose | On Track | Shivam | 0% | 2023-10-02
Traceability Matrix | Med Risk | pooja | 0% | 2023-10-05
Risks | On Track | Gurpreet Kaur | 0% | 2023-10-20
Testing Priorities | Goal | sulika | 0% | 2023-10-20
Risk owner Roles and Responsibilities | Low Risk | pooja | 0% | 2023-09-20
Test Levels | Milestone | Shivam | 0%
Environmental Requirements | Med Risk | pooja | 0%
Acceptance Criteria | High Risk | Gurpreet Kaur | 0%
References | Low Risk | sulika | 0% | 2023-09-22
HIGH LEVEL DESIGN
Purpose | On Track | Shivam | 0% | 2023-10-07
High Level Design | High Risk | Shivam | 0% | 2023-10-07
Design Overview | Milestone | sulika | 0% | 2023-10-07
External Interfaces | Med Risk | sulika | 0% | 2023-10-07
User Interfaces | Milestone | Gurpreet Kaur | 0% | 2023-10-08
Database Organization and Data Storage | High Risk | Gurpreet Kaur | 0% | 2023-10-08
Other Design Considerations | Low Risk | pooja | 0% | 2023-10-09
References Used |  | pooja | 0% | 2023-10-09
UNIT TEST RESULT
Purpose | High Risk | Pooja | 0% | 2023-10-10
Unit Test Cases | Milestone | Gurpreet Kaur | 0% | 2023-10-10
Unit Test Case Results | On Track | sulika | 0% | 2023-10-10
References Used |  | Shivam | 0% | 2023-10-10
INTEGRATION TEST RESULTS
Purpose | High Risk | sulika | 0% | 2023-10-12
Integration Test Plan | Milestone | Shivam | 0% | 2023-10-12
Integration Test Cases | On Track | Pooja | 0% | 2023-10-12
Integration Test Case Results | Goal | Gurpreet Kaur | 0% | 2023-10-12
References Used |  | Gurpreet Kaur | 0% | 2023-10-12
ACCEPTANCE TEST RESULTS
Purpose | High Risk | Gurpreet Kaur | 0% | 2023-10-15
Acceptance Test Plan | Milestone | Pooja | 0% | 2023-10-15
Environment Used | Med Risk | Shivam | 0% | 2023-10-15
Acceptance Test Cases | High Risk | sulika | 0% | 2023-10-15
Acceptance Test Case Results | High Risk | Shivam | 0% | 2023-10-15
References Used |  | Pooja | 0% | 2023-10-15
SYSTEM TEST RESULT
Purpose | High Risk | Gurpreet Kaur | 0% | 2023-10-25
System Test Plan | Med Risk | Pooja | 0% | 2023-10-25
Environment Used | Low Risk | Shivam | 0% | 2023-10-25
System Test Cases | Med Risk | sulika | 0% | 2023-10-25
System Test Case Results | Med Risk | sulika | 0% | 2023-10-25
References Used |  | Pooja | 0% | 2023-10-25
FINAL REPORT
Purpose |  | Pooja | 0% | 2023-11-20
Project Summary |  | Gurpreet Kaur | 0% | 2023-11-20
{Previous Content} |  | Shivam | 0% | 2023-11-20
Traceability Matrix |  | sulika | 0% | 2023-11-20
Conclusions |  | sulika,pooja | 0% | 2023-11-20
Recommendation |  | Gurpreet Kaur,shivam | 0% | 2023-11-20
References Used |  | Pooja | 0% | 2023-11-20
To add more data, Insert new rows ABOVE this one

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. Change the display week number to change the timeline view. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with input messages. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. To remove these instructions from the worksheet, go to Data > Data Tools > Data Validation > Input Message and delete them.
This is the last instruction in this worksheet.